## Sheet1
| Status | Notes | V2 status
4U1UN | OK | 123 days
VE8AT | OK | 117 days | Operational
W6WX | OK3 | 15 days | Operational
KH6RS | OK3 | 363 days | Operational
ZL6B | OK | 161 days
VK6RBP | OK | Although RBN is not hearing the beacon, FAROS ops are seeing it | Club Committed to update but no communications to use to get started
JA2IGY | OK |  | No known owner, no communication, need to get JARL involved
RR9O | OK | 402 days
VR2B | OFF4 | 02-27 - v2 hardware being sent - VR2USP,VR2WQ | Replacement antenna shipped and is in country- install by April end. V2 update will be difficult beause of installation
4S7B | OFF5 | 04-09 - off the air. Thunderstorms again? | Updated to V2, now Transceiver failed. They are trying to repair
ZS6DN | OK | 11 days
5Z4B | OK | 125 days
4X6TU | OK | 513 days
OH2B | OK | 1234 days | Interested, in summer period
CS3B | OFF4 | 03-07 Hardware is ready to ship. Awaiting instructions. Please contact us! | Owner non communicative. Will have to find new location
LU4AA | OFF6 | 02-06 - MIA | V2 shipped and is in country. They are committed to install by April end.
OA4B | OK | 17 days | Interested, not now but soon.
YV5B | OFF6 | 01-18 - MIA | V1 Tranceiver Broken, will upgrade to V2 but we need details
Strategy:
1. Get broken sites updated to V2 and then,
2. Replace hardware at remaining sites.
General Status:
All broken sites contacted. .
Non broken sites not contacted other than OH2B and OA4B. They both indicate interest in V2